AI-POWERED SMART GYM SYSTEM

Sprint Plan & Product Backlog

Must-Have and Should-Have Backlog Items · Organised by Subsystem and Sprint

Derived from the Requirements Engineering specification, translating every Must and Should requirement into an ordered, dependency-aware two-week sprint cadence for a six-student, one-academic-year build.

11 sprints · 2 weeks each · 18 development weeks (Sprints 1 & 3 and 2 & 4 run in parallel)

Mobile application and computer vision: Flutter

Database: Google Cloud Firestore

Wearable: ESP32 + MAX30102 + MPU6500 over Bluetooth Low Energy

# 1. Introduction

## 1.1 Purpose

This document sequences the Must- and Should-priority requirements of the AI-Powered Smart Gym System's Requirements Engineering specification into a delivery plan: eleven two-week sprints for a six-student team working across one academic year. Its purpose is to state, for each sprint, what will be built and why that ordering was chosen — so that a Must item is never scheduled after something that depends on it, and so that supervision, planning and progress tracking share one agreed sequence.

The team's two subteams run Sprints 1 and 3 in parallel during weeks 1–2, and Sprints 2 and 4 in parallel during weeks 3–4 — one subteam on the Auth/Onboarding-then-Data-Layer track, the other on the Computer Vision track — since neither pair depends on the other's output. From week 5 onward every remaining sprint depends on both tracks being in place, so the whole team works through Sprints 5–11 sequentially. This compresses the schedule from eleven sequential slots to nine two-week windows, or 18 development weeks in total.

Every backlog item carries the identifier of the requirement it realises, exactly as numbered in the Requirements Engineering document (Sections 3 and 4). This sprint plan carries no independent numbering scheme for scope: an item's ID is a direct cross-reference, and if a requirement is renumbered, added or removed in that document, this plan is updated to match rather than kept as a separate source of truth.

This revision has been synced to the current Requirements Engineering document. Items dropped from that document (superseded or renumbered) have been removed from the backlog below; FR-NUT-08 has been removed as it is now Could-priority, which is out of scope for this plan; and NFR-SEC-02 (automated Security Rules test coverage) has been added to Sprint 2, since it now appears as a Must-priority requirement with no prior backlog item. Section 3 adds a new Flutter client-side implementation plan, mapping each sprint's backlog to concrete app architecture, packages and modules.

## 1.2 Scope

In scope for this document: the assignment of every Must- and Should-priority functional and non-functional requirement to one of eleven sprints, an overview table giving each sprint's duration and goal, a table of backlog items ordered by priority within each sprint, and a Flutter client-side implementation plan (Section 3).

Out of scope: Could-priority requirements, detailed task breakdown below the backlog-item level, story-point or effort estimation, and individual task assignment within the team's two subteams — these are maintained separately and are not repeated here.

# 2. Sprint Plan

## 2.1 Overview

Eleven two-week sprints across nine two-week windows. Sprints 1 & 3 and Sprints 2 & 4 run in parallel across the team's two subteams; every later sprint runs with the whole team once both tracks are in place. Within this schedule, each subsystem's Must items land before its Should items, and before any later subsystem that depends on it.

| Sprint | Weeks | Team | Goal |
| --- | --- | --- | --- |
| 1 | Weeks 1–2 | Team A | Auth & Onboarding Foundation — Stand up accounts, sign-in and the onboarding flow that every later feature reads from. |
| 3 | Weeks 1–2 | Team B | Computer Vision Core I — Capture & Pose — Get the camera stream, BlazePose and rep/angle math running on-device. |
| 2 | Weeks 3–4 | Team A | Data Layer & Sync — Build the Firestore schema, security rules and offline sync every subsystem will write to. |
| 4 | Weeks 3–4 | Team B | Computer Vision Core II — Feedback & Summaries — Turn pose data into live coaching cues, the skeleton overlay and per-set summaries. |
| 5 | Weeks 5–6 | Whole team | Session Management & Safety — Wrap the CV engine in a structured workout session with rest timers and safety alerts. |
| 6 | Weeks 7–8 | Whole team | Wristband & Biometric Integration — Bring the ESP32 wristband online over BLE and pipe biometrics into the app. |
| 7 | Weeks 9–10 | Whole team | Egyptian Nutrition & Meal Planning — Ship the food catalogue, search, meal-plan generator and logging. |
| 8 | Weeks 11–12 | Whole team | Bilingual Conversational Assistant — Add the domain-restricted chatbot with provider failover and safe context handling. |
| 9 | Weeks 13–14 | Whole team | Localisation & Accessibility — Complete the bilingual UI, RTL mirroring and accessibility baseline. |
| 10 | Weeks 15–16 | Whole team | Analytics, Scalability & Reliability Hardening — Add progress charts and validate the system against its scale and reliability targets. |
| 11 | Weeks 17–18 | Whole team | Compliance, Security Finalisation & Release Readiness — Close out legal, security and packaging work and confirm the whole system fails gracefully. |

## 2.2 Sprint 1 — Auth & Onboarding Foundation

Weeks 1–2 · Team A. Goal: Stand up accounts, sign-in and the onboarding flow that every later feature reads from.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-AUTH-01 | Build the email/password sign-up flow that auto-creates the Firestore profile document at /users/{uid} with the required fields. | Must |
| FR-AUTH-02 | Add email/password and Google Sign-In, resolving both to the same Firebase UID when the verified email matches. | Must |
| FR-AUTH-03 | Implement a self-service password-reset flow that never reveals whether an email address is registered. | Must |
| FR-AUTH-04 | Enforce the password policy (8–32 chars, printable ASCII + space) and let Firebase Auth handle hashing/storage. | Must |
| FR-AUTH-05 | Persist the authenticated session across restarts. | Must |
| FR-PROF-01 | Build an onboarding flow (≤ 8 screens) that collects the eight profile attributes. | Must |
| FR-PROF-02 | Compute and store BMI, refreshed on every height/weight update. | Must |
| FR-PROF-03 | Implement Resting Energy Expenditure via the Mifflin-St Jeor equation. | Must |
| FR-PROF-04 | Derive TDEE and protein/carb/fat targets from REE, activity factor and goal. | Must |
| FR-PROF-07 | Add an in-app Arabic/English language switch that applies without a restart. | Must |
| NFR-SEC-01 | Enforce TLS ≥ 1.2 and certificate pinning on backend endpoints. | Must |
| NFR-SEC-03 | Enforce the NIST-aligned password policy, including a compromised-password check. | Must |
| NFR-MNT-01 | Set up the layered architecture (presentation/domain/data) with no Firestore/camera/plugin dependency in the domain layer. | Must |
| NFR-COMP-01 | Ship one Flutter codebase with documented Android/iOS parity exceptions only. | Must |
| NFR-COMP-02 | Support Android 8.0+ (API 26) and iOS 13+. | Must |
| FR-AUTH-06 | On sign-out, clear the local Isar cache of personal data, biometrics and chat history, keeping only reference data. | Should |
| FR-AUTH-07 | Add an account-deletion flow that recursively removes the /users/{uid} document tree and the Auth record. | Should |
| FR-PROF-05 | Estimate HRmax and derive the five training-intensity zones. | Should |
| FR-PROF-06 | Set a default weekly activity target from activity level and goal, user-overridable. | Should |

## 2.3 Sprint 3 — Computer Vision Core I — Capture & Pose

Weeks 1–2 · Team B. Goal: Get the camera stream, BlazePose and rep/angle math running on-device.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-CV-01 | Wire up a live camera stream at ≥ 720p/30fps. | Must |
| FR-CV-02 | Integrate on-device BlazePose to extract 33 landmarks and world landmarks per frame. | Must |
| FR-CV-03 | Support Lite/Full/Heavy model variants with device-tier auto-selection and a manual override. | Must |
| FR-CV-04 | Compute joint angles (knee, hip, trunk, elbow, shoulder) in Dart via 2-D vector trigonometry. | Must |
| FR-CV-05 | Implement per-exercise repetition counting using hysteresis thresholds. | Must |
| FR-CV-06 | Build the posture risk-scoring rule set (knee valgus, ROM/depth, lumbar flexion, forward lean, elbow flare, asymmetry). | Must |
| NFR-PERF-01 | Keep on-device pose inference ≤ 30 ms/frame, sustaining ≥ 25 fps during an active set. | Must |
| NFR-PERF-10 | Keep camera preview latency (movement to screen) ≤ 100 ms. | Must |
| NFR-COMP-03 | Require ≥ 3 GB RAM + 720p/30fps camera for pose coaching; disable cleanly below spec. | Must |
| NFR-SEC-04 | Guarantee no raw camera frame, image or video ever leaves the device, including crash/diagnostic uploads. | Must |

## 2.4 Sprint 2 — Data Layer & Sync

Weeks 3–4 · Team A. Goal: Build the Firestore schema, security rules and offline sync every subsystem will write to.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-DATA-01 | Stand up the Firestore collection structure (/users, /workouts, /sets, /biometrics, /meals, /chat, /foods, /exercises, /appConfig, /auditLog). | Must |
| FR-DATA-02 | Give every document a schemaVersion integer and a serverTimestamp updatedAt field. | Must |
| FR-DATA-03 | Enable Firestore offline persistence — cached reads, durably queued offline writes. | Must |
| FR-DATA-04 | Aggregate biometric samples into fixed time-window documents rather than one per sample. | Must |
| FR-DATA-05 | Use batched writes/transactions for multi-document updates, within the per-commit limit. | Must |
| FR-DATA-06 | Write deny-by-default Security Rules scoping each client to its own /users/{uid} subtree. | Must |
| NFR-SCAL-02 | Keep reads/writes at 500 DAU (Daily Active Users) inside the Firestore free tier. | Must |
| NFR-SCAL-04 | Model unbounded lists as subcollections to avoid the 1 MiB document limit. | Must |
| NFR-SEC-02 | Cover the deny-by-default Security Rules with an automated test suite, including cross-user. | Must |
| NFR-PERF-12 | Commit biometrics as one aggregated document per 60 s window per user, never per sample. | Must |
| FR-DATA-07 | Mirror food/exercise catalogues into local storage at launch for offline search, refreshed on version mismatch. | Should |
| FR-DATA-08 | Define composite indexes in advance for every planned query. | Should |
| NFR-SCAL-01 | Confirm the architecture supports 5,000 accounts / 500 DAU without change. | Should |
| NFR-PERF-05 | Acknowledge writes locally at once; commit to Firestore within 500 ms p95 on 4G. | Should |

## 2.5 Sprint 4 — Computer Vision Core II — Feedback & Summaries

Weeks 3–4 · Team B. Goal: Turn pose data into live coaching cues, the skeleton overlay and per-set summaries.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-CV-07 | Deliver real-time corrective feedback via synchronised TTS and on-screen overlay, rate-limited to one cue per 2s. | Must |
| FR-CV-08 | Render the colour-coded (green/amber/red) skeleton overlay on the camera preview. | Must |
| FR-CV-09 | Discard low-visibility landmarks; suspend scoring and prompt repositioning after 1s of missing landmarks. | Must |
| FR-CV-10 | Add a pre-set framing calibration with a 3-second audible countdown before scoring begins. | Must |
| FR-CV-11 | Guarantee no raw frame, image, video or per-frame landmark stream is ever transmitted or persisted. | Must |
| FR-CV-12 | Ship the v1 exercise library: squat, deadlift, bench press. | Must |
| FR-CV-14 | Produce the per-set summary — reps, time-under-tension, ROM, tempo, form score, fault counts. | Must |
| NFR-PERF-02 | Keep feedback latency ≤ 100 ms to the overlay and ≤ 300 ms to the spoken cue. | Must |
| NFR-PERF-08 | Keep app start ≤ 3 s cold, ≤ 1.5 s warm, ≤ 1 s hot. | Must |
| FR-CV-13 | Monitor inference frame rate and auto-downgrade model/resolution if it drops below the performance floor for 3s. | Should |
| NFR-PWR-05 | Downgrade model/rate before the platform throttles, avoiding sustained thermal throttling in a 45-minute session. | Should |

## 2.6 Sprint 5 — Session Management & Safety

Weeks 5–6 · Whole team. Goal: Wrap the CV engine in a structured workout session with rest timers and safety alerts.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-ALRT-01 | Model a workout as an ordered exercise list with sets/reps/load and per-set completion tracking. | Must |
| FR-ALRT-02 | Add an automatic inter-set rest timer. | Must |
| NFR-REL-02 | Keep coaching, set logging, rest timer and food logging fully usable offline with zero data loss. | Must |
| FR-ALRT-03 | Raise a caution when heart rate exceeds 90% of estimated HRmax. | Should |
| FR-ALRT-04 | Show a warm-up recommendation and a mandatory first-session safety acknowledgement. | Should |

## 2.7 Sprint 6 — Wristband & Biometric Integration

Weeks 7–8 · Whole team. Goal: Bring the ESP32 wristband online over BLE and pipe biometrics into the app.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| NFR-COMP-04 | Require BLE 4.2+ for the wristband link; its absence disables only biometric features. | Must |
| NFR-REL-04 | Re-establish the wristband link within 10 s of returning to range. | Should |
| NFR-PWR-01 | Target ≥ 8 h continuous session use per charge. | Should |
| NFR-PWR-06 | Have the wristband enter deep sleep when battery voltage stays ≤ 2.95 V for 5 consecutive readings. | Should |
| NFR-PERF-04 | Surface a biometric sample in the UI within 200 ms of its generation on the band. | Should |
| NFR-PERF-11 | Sample the optical sensor at ≈ 100 sps while the band is connected. | Should |

## 2.8 Sprint 7 — Egyptian Nutrition & Meal Planning

Weeks 9–10 · Whole team. Goal: Ship the food catalogue, search, meal-plan generator and logging.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-NUT-01 | Load the curated Egyptian food catalogue (≥ 300 entries, named staples). | Must |
| FR-NUT-02 | Give every food entry bilingual names, category, per-100g macros and ≥ 1 household portion. | Must |
| FR-NUT-04 | Implement fuzzy Arabic/English/transliterated food search. | Must |
| FR-NUT-05 | Build the daily meal-plan generator (3 meals + ≤ 2 snacks, TDEE ± 5%, protein ± 10%). | Must |
| FR-NUT-07 | Add food logging (search / portion / repeat-yesterday) with running daily totals. | Must |
| FR-NUT-09 | Record dietary exclusions and enforce them in every generated plan. | Must |
| NFR-DQ-04 | Ensure ≥ 95% of catalogue entries have complete macros and 100% carry a source reference. | Must |
| FR-NUT-03 | Attach an indicative EGP price with a priceAsOf date; flag entries stale after 90 days. | Should |
| FR-NUT-06 | Show estimated plan cost in EGP; allow regeneration under a stated daily budget ceiling. | Should |
| NFR-DQ-05 | Prefer the national composition table over a generic international one for indigenous dishes. | Should |
| NFR-PERF-09 | Return local food search results within 500 ms of the last keystroke. | Should |

## 2.9 Sprint 8 — Bilingual Conversational Assistant

Weeks 11–12 · Whole team. Goal: Add the domain-restricted chatbot with provider failover and safe context handling.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-CHAT-01 | Detect the message language and reply in matching MSA / Egyptian Arabic / English. | Must |
| FR-CHAT-03 | Constrain the assistant to fitness/nutrition/safety topics; decline out-of-domain requests politely. | Must |
| FR-CHAT-04 | Inject goal, experience, limitations, recent workout summary and macro targets as context (never raw biometric series). | Must |
| FR-CHAT-06 | Refuse medical diagnosis/prescription and show a persistent non-diagnostic disclaimer. | Must |
| FR-CHAT-07 | Persist chat history (role, content, language, model, tokens, timestamp) under /users/{uid}/chat, with a clear-history option. | Must |
| NFR-SEC-05 | Proxy all LLM calls through the backend; embed no third-party API credentials client-side. | Must |
| NFR-SEC-06 | Strip direct identifiers from chat text before transmission, disclosed in the consent flow. | Must |
| NFR-SEC-11 | Rate-limit chat completions server-side, per user and per IP. | Must |
| NFR-REL-05 | Fail over to the secondary LLM provider if no first token arrives within 5 s. | Must |
| FR-CHAT-02 | Add primary-to-secondary LLM provider failover on error, timeout or rate-limit. | Should |
| FR-CHAT-05 | Stream the reply to the client. | Should |
| FR-CHAT-08 | Return a cached/templated fallback for common intents when both providers are unavailable. | Should |
| NFR-SEC-09 | Write a documented breach-response procedure. | Should |
| NFR-PERF-07 | Start streaming a chat reply within 1.5 s p95; finish a 150-token reply within 3 s. | Should |

## 2.10 Sprint 9 — Localisation & Accessibility

Weeks 13–14 · Whole team. Goal: Complete the bilingual UI, RTL mirroring and accessibility baseline.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-LOC-01 | Build the complete Arabic + English UI. | Must |
| FR-LOC-02 | Fully mirror layout — nav, icons, charts, lists — in RTL for Arabic. | Must |
| FR-LOC-03 | Localise numerals and format dates/time/currency to the Egyptian locale. | Must |
| FR-LOC-05 | Replace raw exceptions/stack traces with localised, actionable error messages. | Must |
| NFR-USE-04 | Meet ≥ 4.5:1 text contrast in both themes and both languages. | Must |
| NFR-USE-05 | Keep every pointer target ≥ 44×44 logical pixels. | Must |
| FR-LOC-04 | Record spoken coaching cues in both languages, Arabic in Egyptian phrasing. | Should |
| NFR-USE-06 | Have ≥ 4 native reviewers judge the Arabic UI as natural, not a literal translation. | Should |
| NFR-USE-07 | Verify coaching cues are intelligible over gym noise, with a visual counterpart for every audio cue. | Should |
| NFR-USE-08 | Keep every screen’s primary task readable in ≤ 40 words. | Should |

## 2.11 Sprint 10 — Analytics, Scalability & Reliability Hardening

Weeks 15–16 · Whole team. Goal: Add progress charts and validate the system against its scale and reliability targets.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| FR-ANL-03 | Chart mean form score per exercise over time. | Should |
| FR-ANL-04 | Chart HR trends per session and resting HR over time, from stored aggregates. | Should |
| FR-ANL-05 | Track adherence — sessions completed vs. planned, minutes vs. weekly target. | Should |
| NFR-DQ-01 | Validate reported HR against a chest-strap reference within ± 10 bpm for ≥ 90% of paired samples. | Should |
| NFR-DQ-03 | Validate rep-counting (≥ 95%) and fault-classification (≥ 90%) accuracy against labelled ground truth. | Should |
| NFR-SCAL-07 | Confirm search stays fast at 2,000 food / 100 exercise catalogue entries. | Should |
| NFR-SCAL-08 | Cap and prune chat history per user to bound storage growth. | Should |
| NFR-REL-01 | Track the cloud data tier against the ≥ 99.9% monthly availability target. | Should |
| NFR-USE-03 | Keep starting a tracked set from the home screen to ≤ 3 taps. | Should |

## 2.12 Sprint 11 — Compliance, Security Finalisation & Release Readiness

Weeks 17–18 · Whole team. Goal: Close out legal, security and packaging work and confirm the whole system fails gracefully.

| ID | Backlog Item | Priority |
| --- | --- | --- |
| NFR-LEG-01 | State prominently, at onboarding and in settings, that this is a wellness aid, not a medical device. | Must |
| NFR-LEG-02 | Base data processing on explicit, per-purpose consent, with access/correct/erase/object/withdraw support. | Must |
| NFR-LEG-03 | Handle health data as a special category with enhanced safeguards. | Must |
| NFR-LEG-05 | Keep coaching/nutrition guidance within general-wellness advice; decline injury/condition-specific advice. | Must |
| NFR-REL-09 | Verify no single failure (band, network, either LLM provider, camera permission) cascades beyond its own feature. | Must |
| NFR-SEC-07 | Retain biometric window documents ≤ 12 months, then aggregates only. | Should |
| NFR-SEC-08 | Document the database region and disclose any cross-border transfer. | Should |
| NFR-SEC-12 | Log all admin actions on shared catalogues to an append-only, user-unwritable audit log. | Should |
| NFR-LEG-04 | Ship an open-source notices screen honouring third-party licence obligations. | Should |
| NFR-LEG-06 | Keep activity recommendations within WHO weekly-minute guidance. | Should |
| NFR-MNT-02 | Reach ≥ 70% domain-layer unit-test coverage. | Should |
| NFR-MNT-03 | Keep exercise rules/cues as declarative configuration, not branching code. | Should |
| NFR-MNT-05 | Document a one-command reproducible build per component. | Should |
| NFR-MNT-06 | Make diagnostic logging structured, off by default in release, and free of personal/biometric data. | Should |
| NFR-PERF-13 | Keep the Android bundle ≤ 60 MB including the bundled pose model. | Should |